## Summary
Summary of Bug Categorization
Build Receive Date | Rounds | Bugs Reporting Date | Total No of Bugs | New Bug | Re-Opened Bug | Suggestion
2017-10-12 | 1 | 2017-10-18 | 7 | 7 | 0 | 0
DotNet Total | 1 |  | 7 | 7 | 0 | 0
Staging Total | 0 |  | 0 |  | 0 | 0
Production Total | 0 |  | 0 | 0 | 0 | 0
Total | 1 |  | 7 | 7 | 0 | 0
User Interface Total | User Experience Total | Performance Total | Functional Total | Requirement | Total
4 | 0 | 0 | 3 | 0 | 7
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Production
DotNet
Staging

## Test Case Round1
Company Icon | Company Name | Test Case
Start Date : | 2017-10-12 | Project: |  | End Date : | 2017-10-18
Tested by: | Yogesh | Platform: | Kiosk | Round : | 1
Build Version: | 1.1.1 | Server: | Development | Review By :
Device Name/Machine IP: | Cellular iPad | OS: | 9.1
Test Case Id | Test Case Summary | Prerequisites | Test Procedure (Steps) | Test Data | Expected Result | Actual Data | Status
EESKT_01 | Customize Question Name changed every time in Report when Reset Program. | 1. Wi-Fi network must be on. 2. Application must be install. 3. User and Child must be Created in EESK application. | 1.Tap on Application. 2.Enter valid username and password. => Tap on Sign in button. 3.Tap on Go to Admin Mode. 4.Programs => Tap on Assign -> Select Learn to Sit program. => Continue -> Select Learn to Sit program option. 5. In EDIT TRIAL ->Tap on EDIT button. => Answer to customize. => Tap on "Submit" button. 6. Tap on "TEXT PROMPT" => In Change Question popup box => Change text "sit" => Tap on "Save" button. => Tap on "Resume" button. 7. Now verified the text in program => Tap on "YES" => Tap on "Next" => Tap ">" twice => Now tap "<"(Back) button. => Answer to customize. => Tap on "Submit" button. 8. Tap on Reports => Tap on "Learn to Sit" program. => Tap on last played program => Verified the Question Name is "Sit". | 1.Username : et1001 2.Password : et1001 | Customize Question Name should not changed every time in Report when Reset Program. | Same as Expected | Pass
EESKT_02 | Title of Prompt should not be editable. | 1. Wi-Fi network must be on. 2. Application must be install. 3. User and Child must be Created in EESK application. | 1.Tap on Application. 2.Enter valid username and password. => Tap on Sign in button. 3.Tap on Go to Admin Mode. 4.Programs => Tap on Assign -> Select Learn to Sit program. => Continue -> Select Learn to Sit program option. 5. In EDIT TRIAL ->Tap on EDIT button. => Answer to costomize. => Tap on "Submit" button. 6. Tap on "T PROMPT" => User can change the text. Title of Prompt should not be editable. | 1.Username : et1001 2.Password : et1001 | Title of Prompt should not be editable. | Same as Expected | Fail
EESKT_03 | Sound Icon is missing in Prompt. | 1. Wi-Fi network must be on. 2. Application must be install. 3. User and Child must be Created in EESK application. | 1.Tap on Application. 2.Enter valid username and password. => Tap on Sign in button. 3.Tap on Go to Admin Mode. 4.Programs => Tap on Assign -> Select Learn to Sit program. => Continue -> Select Learn to Sit program option. 5. In EDIT TRIAL ->Tap on EDIT button. => Answer to costomize. => Tap on "Submit" button. 6. Verify the title Sound icon is missing. | 1.Username : et1001 2.Password : et1001 | Sound Icon is missing in Prompt. | Same as Expected | Pass
EESKT_04 | Testing Comment display in Report. | 1. Wi-Fi network must be on. 2. Application must be install. 3. User and Child must be Created in EESK application. | 1.Tap on Application. 2.Enter valid username and password. => Tap on Sign in button. 3.Tap on Go to Admin Mode. 4.Programs => Tap on Assign -> Select "State the action" program. => Tap on "<"(Back) option. 5. Tap on "Customize" button. => Tap on "Learn to Sit" program. => Select "Program Content" => Tap on Select All "Uncheck" all => Tap 1st Question on Edit 6. Tap on "<"(Back) option. 7. Now verify the select all checkbox checked all. | 1.Username : et1001 2.Password : et1001 | Testing Comment display in Report. | Same as Expected | Pass
EESKT_05 | Selected all Checkbox automatically changed. | 1. Wi-Fi network must be on. 2. Application must be install. 3. User and Child must be Created in EESK application. | 1.Tap on Application. 2.Enter valid username and password. => Tap on Sign in button. 3.Tap on Go to Admin Mode. 4.Programs => Tap on Assign -> Select "State the action" program. => Tap on "<"(Back) option. 5. Tap on "Customize" button. => Tap on "Learn to Sit" program. => Select "Program Content" => Tap on Select All "Uncheck" all => Tap 1st Question on Edit 6. Tap on "<"(Back) option. 7. Now verify the select all checkbox checked all. | 1.Username : et1001 2.Password : et1001 | Selected all Checkbox automatically changed. | Selected all Checkbox should not automatically changed. | Pass
EESKT_06 | "Record" text remove from Custom Edit in parent assistant program | 1. Wi-Fi network must be on. 2. Application must be install. 3. User and Child must be Created in EESK application. | 1.Tap on Application. 2.Enter valid username and password. => Tap on Sign in button. 3.Tap on Go to Admin Mode. 4.Programs => Tap on Assign -> Select "State the action" program. => Tap on "<"(Back) option. 5. Tap on "Customize" button. => Tap on "Learn to Sit" program. => Select "Program Content" => Tap on Select All "Uncheck" all => Tap 1st Question on Edit 6. Tap on "<"(Back) option. 7. Now verify the select all checkbox checked all. | 1.Username : et1001 2.Password : et1001 | "Record" text remove from Custom Edit in parent assistant program | "Record" text remove from Custom Edit in parent assistant program | Pass
EESKT_07 | Application hang when click on "Save" button. | 1. Wi-Fi network must be on. 2. Application must be install. 3. User and Child must be Created in EESK application. | 1.Tap on Application. 2.Enter valid username and password. => Tap on Sign in button. 3.Tap on Go to Admin Mode. 4.Programs => Tap on Assign -> Select "State the action" program. => Tap on "<"(Back) option. 5. Tap on "Customize" button. => Tap on "Learn to Sit" program. => Select "Program Content" => Tap on Select All "Uncheck" all 6. Tap on "Save" button. => "No assigned question is found to save" alert tap on "OK" 7. Now Loading... progressbar display. | 1.Username : et1001 2.Password : et1001 | Application hang when click on "Save" button. | Application hang when click on "Save" button. | Fail
EESKT_08 | Showing different Version in application. | 1. Wi-Fi network must be on. 2. Application must be install. 3. User and Child must be Created in EESK application. | 1.Tap on Application. 2.Tap on "i"(info) button 3. Now verify the version is different than mail. | 1.Username : et1001 2.Password : et1001 | Showing different Version application info. | Showing different Version application info. | Fail

## Defect Report Round1
Company Icon | Company Name | Defect Report | [17 empty] | New Bug
Re-Open Bug
Start Date : | 2017-10-12 | Project: |  | End Date : | 2017-10-18 | [14 empty] | Suggestion
Tested by: |  | Platform: | iOS | Round : | 1
Build Version: | 1.1.1 | Server: | Production | Review By :
Device Name/Machine IP: | Cellular iPad | OS: | 9.1
Defect Id | Defect Description | Steps to Reproduce | Actual Result | Expected Result | Attachments/Screen-shots | Severity | Priority | Status | Type | Type of Bug | User Interface Total | User Experience Total | Performance Total | Functional Total | Requirement Total | New BugTotal | Re-Open Bug Total | Suggestion Total | Total Bug
EESKD_01 | In Report Customize Question Name changed every time when Reset Program. | Steps to Produce :- 1.Tap on Application. 2.Enter valid username and password. => Tap on Sign in button. 3.Tap on Go to Admin Mode. 4.Programs => Tap on Assign -> Select Learn to Sit program. => Continue -> Select Learn to Sit program option. 5. In EDIT TRIAL ->Tap on EDIT button. => Answer to customize. => Tap on "Submit" button. 6. Tap on "TEXT PROMPT" => In Change Question popup box => Change text "sit"=> Tap on "Save" button.=> Tap on "Resume" button. => Now verified the text in program => Tap on "YES"=> Tap on "Next" => Tap ">" twice=> Now tap "<"(Back) button.=> Answer to customize. => Tap on "Submit" button. 7. Tap on Reports => Tap on "Learn to Sit" program. => Tap on last played program => Verified the Question Name is "Sit" -> tap on Cancel. => Tap on "<-"(Back) twice button. 8. Tap on "Customize" button. => Tap on "Learn to Sit" program. => Select "Reset Program" => Tap on "<-"(Back) button. Now follow the step 7 and verified result. | Customize Question Name changed every time in Report when Reset Program. | Customize Question Name should not changed every time in Report when Reset Program. |  | High | 1 | New | Funcational | New Bug | 4 | 0 | 0 | 3 | 0 | 7 | 0 | 0 | 7
EESKD_02 | Title of Prompt should not be editable. | 1.Tap on Application. 2.Enter valid username and password. => Tap on Sign in button. 3.Tap on Go to Admin Mode. 4.Programs => Tap on Assign -> Select Learn to Sit program. => Continue -> Select Learn to Sit program option. 5. In EDIT TRIAL ->Tap on EDIT button. => Answer to costomize. => Tap on "Submit" button. 6. Tap on "T PROMPT" => User can change the text. Title of Prompt should not be editable. | Title of Prompt should not be editable. | Title of Prompt should not be editable. | 2.jpg | High | 1 | New | User Interface | New Bug
EESKD_03 | Sound Icon is missing in Prompt. | 1.Tap on Application. 2.Enter valid username and password. => Tap on Sign in button. 3.Tap on Go to Admin Mode. 4.Programs => Tap on Assign -> Select Learn to Sit program. => Continue -> Select Learn to Sit program option. 5. In EDIT TRIAL ->Tap on EDIT button. => Answer to costomize. => Tap on "Submit" button. 6. Verify the title Sound icon is missing. | Sound Icon is missing in Prompt. | Sound Icon is missing in Prompt. | 3.jpg | High | 1 | New | User Interface | New Bug
EESKD_04 | Selected all Checkbox automatically changed. | 1.Tap on Application. 2.Enter valid username and password. => Tap on Sign in button. 3.Tap on Go to Admin Mode. 4.Programs => Tap on Assign -> Select "State the action" program. => Tap on "<"(Back) option. 5. Tap on "Customize" button. => Tap on "Learn to Sit" program. => Select "Program Content" => Tap on Select All "Uncheck" all => Tap 1st Question on Edit 6. Tap on "<"(Back) option. 7. Now verify the select all checkbox checked all. | Selected all Checkbox automaticaly changed. | Selected all Checkbox should not automatically changed. |  | Medium | 3 | New | Funcational | New Bug
EESKD_05 | "Record" text should be remove from Custom Edit in parent assistant program. | 1.Tap on Application. 2.Enter valid username and password. => Tap on Sign in button. 3.Tap on Go to Admin Mode. 4.Programs => Tap on Assign -> Select Learn to Sit program. => Continue -> Select Learn to Sit program option. 5. In EDIT TRIAL ->Tap on EDIT button. => Answer to costomize. => Tap on "Submit" button. 6. Verify the title Sound icon is missing. | "Record" text remove from Custom Edit in parent assistant program | "Record" text remove from Custom Edit in parent assistant program | 5.jpg | Low | 3 | New | User Interface | New Bug
EESKD_06 | Application hang when click on "Save" button. | 1.Tap on Application. 2.Enter valid username and password. => Tap on Sign in button. 3.Tap on Go to Admin Mode. 4.Programs => Tap on Assign -> Select "State the action" program. => Tap on "<"(Back) option. 5. Tap on "Customize" button. => Tap on "Learn to Sit" program. => Select "Program Content" => Tap on Select All "Uncheck" all 6. Tap on "Save" button. => "No assigned question is found to save" alert tap on "OK" 7. Now Loading... progressbar display. | Application hang when click on "Save" button. | Application hang when click on "Save" button. | 6.jpg | High | 1 | New | Funcational | New Bug
EESKD_07 | Showing different Version in application info. | 1.Tap on Application. 2.Tap on "i"(info) button 3. Now verify the version is different than mail. | Showing different Version in application info. | Version should be same as email description. | 7.jpg | Low | 1 | New | User Interface | New Bug

## dropdown (hidden)
list01 | list02 | list03 | list04 | list05 | list06 | list07 | list08 | list09 | list10 | list11
iOS | Time Card | Hardeep | 1.0.0 | Development | High | 1 | New | Android | User Interface | Pass
Android | HEKXO App and Web | Bhavin | 1.1.1 | Staging | Medium | 2 | Open | 1.6 | User Experience | Fail
Web | ColorsKit - Admin | Yogesh | 1.1.2 | Production | Low | 3 | Re-opened | 2.1 | Perfomace | None
Kiosk | Rangam Consultants Inc. | Sahil | 1.1.3 |  |  |  | Closed | 2.2 | Funcational
| The Spectrum Careers (App and Web) | Kedar | 1.1.4 |  |  |  | In discussion | 2.3 | Requirement
| OnBoarding App and Web | Angad | 1.1.5 |  |  |  |  | 3
| ColorsKit - Early Education School Kit |  | 1.1.6 |  |  |  |  | 4
| ColorsKit - Early Education Home Kit |  | 1.1.7 |  |  |  |  | 4.1
| ColorsKit - Life Skill Home/School Kit |  | 1.1.8 |  |  |  |  | 4.4
| The Spectrum Careers - UK (App and Web) |  | 1.1.9 |  |  |  |  | 5
| WebTeam Corp |  | 2.0.0 |  |  |  |  | 6
| Special Game Changer |  | 2.0.1 |  |  |  |  | 7
| Rangam Intranet |  | 2.0.2 |  |  |  |  | iOS
| Tricky Water |  | 2.0.3 |  |  |  |  | 4.4
| Rangam Infotech Pvt Ltd. |  | 2.0.4 |  |  |  |  | 4.5
| LetUsConnect |  | 2.0.5 |  |  |  |  | 4.6
| SAMHIN |  | 2.0.6 |  |  |  |  | 4.7
| Lapiz Lazooli |  | 2.0.7 |  |  |  |  | 4.8
| Haribhakti Trust |  | 2.0.8 |  |  |  |  | 4.9
| Staffing Bulletin |  | 2.0.9 |  |  |  |  | 4.1
| Rangam Staffing Pvt. Ltd. | [6 empty] | 5.1
| Jannya App and Web | [6 empty] | 5.2
| My Event Day (App and Web) | [6 empty] | 5.3
| Innovation and Technology | [6 empty] | 5.4
| ColorsKit Apps and Web | [6 empty] | 6.1
| ProCricket America | [6 empty] | 7.1
| SourcePros | [6 empty] | 7.2
| Client Work | [6 empty] | 9.1
| Organizational Operation | [6 empty] | 9.2
| Shanesh Colors (Kiosk/Colors Program) | [6 empty] | 9.3
| HEKXO Kickstarter | [6 empty] | 9.4
| In House Development Projct | [6 empty] | 9.5
| ColorsKit Supplemental Apps | [6 empty] | 9.6
HrTeamPlus
IAGSC
My Idea Portal
ColorsKit - MyToday
Other