## Summary
Summary of Bug Categorization | [5 empty] | Summary of Bug Categorization
[7 empty] | Round | User Interface Total | User Experience Total | Performance Total | Functional Total | Requirement Total
[7 empty] | 2 | 1 | 4 | 0 | 4 | 3
[7 empty] | 3 | 2 | 5 | 0 | 5 | 0
Build Receive Date | Rounds | Bugs Reporting Date | Total No of Bugs | Re-Opened Bug | Suggestion
13/09/2016 | 2 | 19/09/2016 | 12 | 1 | 0
20/09/2016 | 3 | 21/09/2016 | 12 | 1 | 0
DotNet Total | 3 |  | 24 | 2 | 0
Build Receive Date | Rounds | Bugs Reporting Date | Total No of Bugs | Re-Opened Bug | Suggestion
Staging Total | 0 |  | 0 | 0 | 0
Build Receive Date | Rounds | Bugs Reporting Date | Total No of Bugs | Re-Opened Bug | Suggestion
Production Total | 0 |  | 0 | 0 | 0
Total | 0 |  | 24 | 2 | 0
DotNet
Staging
Production

## Test Case
| Rangam Technologies | Test Case | SD/F/1/19
Start Date : | 13/09/2016 | Project: | ColorsKit - Life Skill Home/School Kit | End Date : | 27/04/2016
Tested by: | Bhavin | Platform: | Android | Round : | 2
Build Version: | 2.0.0 | Server: | Development
Device Version: | Samsung | OS: | 4.1
Test Case Id | Test Case Summary | Prerequisites | Test Procedure (Steps) | Test Data | Expected Result | Actual Data | Status
CT_01 | To verify login functionality | User have installed clip board app and user id on Life Skill app. | 1.Enter valid Usre name. 2.Enter valid password. 3.Tap on Sign in. | User name :- rangamclip Password :- rangam@123 | User have logged in successfully. | As Expected | Pass
CT_02 | To verify Add New Behavior |  | 1.Tap on "New Behavior" on Behaviors list. On Name and Details Tab 2.Enter valid Behavior Name. 3.Enter valid Details. 4.Enter valid upload file. On Data Recording Method 5.Select any method you want. On Notification and Settings 6.Tap on 'Submit'. | Behavior Name : 14th Sept. Demo Freq. Details : some text File : Valid image, audio,video,document file. Method : By default Frequency/Rate Selected. | Behavior created successfully and this behavior shown on behavior list. | As Expected | Pass
CT_03 | To verify Edit Behavior | Behavior would not assigned. | On Behaviors 1.Tap in Edit. 2.Update details. Data Recording Method Tab 3.All the selection disabled. Notification and Settings 4.Tap on 'Submit'. | Behavior Name : 14th Sept. Demo Freq. edited. Details : some text File : Valid image, audio,video,document file. | Behavior edited successfully. | As Expected | Pass
CT_04 | To verify Delete Behavior | Behavior should be created and not assigned. | On Behaviors 1.Tap on Delete symbol. 2.Tap on "Ok". | NA | Behavior Delete successfully. | As Expected | Pass
CT_05 | To verify record behavior assign behavior | Behavior should be created and assign. | On Behaviors 1.Tap on Checkbox to assign behavior. | NA | Behavior assign successfully and this behavior shown in Solo Data Sheet -> Behavior tab. | As Expected | Pass
CT_06 | To verify Record the frequency behavior | Behavior should be created and assigned. | On App's Dashboard 1.Tap on Solo Data Sheet. 2.Tap on Behavior. 3.Tap on Start Observation. 4.Tap on (+) symbol to record observation. | NA | Frequency data recorded. | As Expected (Data is not accurate) | Pass
CT_07 | To verify Reports and graph of frequency | Frequency should be recorded. | On App's Dashboard 1.Tap on Reports and Graphs. 2.Tap on freq.demo-> More Details 3.Tap on chart. | NA | Reports and chart shown successfully. | On the chart also once again "View Chart" shown. | Fail
CT_08 | To verify Duration Method Rreocording | Behavior should be created and duration method selected. | On App's Dashboard 1.Tap on Solo Data Sheet. 2.Tap on Start Observation. 3. After some time, Stop Observation. | NA | Duration Recorded Successfully. | Duration not recorded successfully.In duration value never change. | Fail
CT_09 | To verify Reports and graph for Duration Method | Duration should be recorded. | On App's Dashboard 1.Tap on Reports and Graphs. 2.Tap on Duration demo-> More Details 3.Tap on chart. | NA | Reports and chart shown successfully. | Duration calculation is not proper show graph report also shown wrong. | Fail
CT_10 | To verify Latency Method Assigned | Latency Behavior should be created and assigned. | On Behaviors 1.Tap on Checkbox to assign Latency behavior. | NA | Behavior assign successfully and this behavior shown in Solo Data Sheet -> Behavior tab. | As Expecteed | pass
CT_11 | To verify Latency Method Reocording | Behavior should be created and latency method selected. | On App's Dashboard 1.Tap on Solo Data Sheet. 2.Tap on Play Symbol. 3. After some time, tap on stop symbol. | NA | Frequency Recorded Successfully. | As Expected | Pass
CT_12 | To verify create schedule interval behaviour method | User have installed app and have a login id. | On App's Dashboard 1.Tap on Behaviour. 2.Tap on Plus Symbol. On Name and Detials, 3. Add valid details. On Data Recording Method, 4.Tap on Method Interval. 5.Tap on Method Settings. 6.Tap on From and To and select time. 7.Set Interval Time. | Behavior Name :- 14th. Sept. schedule Method :- Interval Method Settings :- Schedule Interval From: 9:00 AM To: 1:00 PM Interval : 60 minutes | Schedule Interval created and shown in behavior list. | When set interval time alert message shown "Please set end time at least 10 min larger than start time". | Fail
CT_13 | To verify create Manual Interval | User have installed app and have a login id. | On App's Dashboard 1.Tap on Behaviour. 2.Tap on Plus Symbol. On Name and Detials, 3. Add valid details. On Data Recording Method, 4.Tap on Method Interval. 5.Tap on Manual Interval Method Settings. 6.Set Interval Time. On Notification and Settings 1.Tap on 'Submit'. | Behavior Name :- 14th. Sept. manual interval Method :- Interval Method Settings :- Manual Interval Interval : 10 minutes | Manual interval behavior method created and shown in behaviors list. | As Expected. | Pass
CT_14 | To verify Manual Interval assigned | Manual Interval Behavior should be created and assigned. | On Behaviors 1.Tap on Checkbox to assign Latency behavior. | NA | Behavior assign successfully and this behavior shown in Solo Data Sheet -> Behavior tab. | As Expected | Pass
CT_15 | To verify Manual Interval Method Reocording | Behavior should be created and Manual Interval method selected. | 1.Tap on "Start" Symbol. 2. In mean time tap on data recorded. | NA | Manual interval recorded. | As Expected (Demo Purpose not working) | Pass

## Defect Report Round1
| Rangam Technologies | Defect Report | [17 empty] | New Bug
Re-Open Bug
Start Date : | 13/09/2016 | Project: | ColorsKit - Life Skill Home/School Kit | End Date : | 19/09/2016 | [14 empty] | Suggestion
Tested by: | Bhavin | Platform: | Android | Round : | 2
Build Version: | 2.0.0 | Server: | Development
Device Version: | Samsung | OS: | 4.4
Defect Id | Defect Description | Steps to Reproduce | Actual Result | Expected Result | Attachments/Screen-shots | Severity | Priority | Status | Type | Type of Bug | User Interface Total | User Experience Total | Performance Total | Functional Total | Requirement Total | New BugTotal | Re-Open Bug Total | Suggestion Total | Total Bug
CD_01 | UI issue on Reports and Graph section. | On App's Dashboard 1.Tap on Reports and Graphs. 2.Tap on freq. -> More details. 3.View Chart. | On view chart once again view chart shown. | On "View Chart" -> "View Chart" not shown. |  | High | 1 | New | User Interface | New Bug | 1 | 4 | 0 | 4 | 3 | 11 | 1 | 0 | 12
CD_02 | Frequency not accurate when interval time difference | On app's Dashboard 1.Tap on Solo Data Sheet 2.Record frequency behavior within short time. | Data not accurate recorded. | Data recorded in any interval it should be accurate. |  | High | 1 | Re-opened | Requirement | Re-Open Bug
CD_03 | Duration Not recorded accurate | On app's Dashboard 1.Tap on Solo Data Sheet 2.Record Duration behavior within short time. | Data not accurate recorded. | Data recorded in any interval it should be accurate. |  | High | 1 | New | Funcational | New Bug
CD_04 | Duration not shown proper if user has just start and immediately stop observation. At that time if data not recorded than it should not shown (00:00:00) | On app's Dashboard 1.Tap on Solo Data Sheet 2.Tap on Start Observation. 3.Without tap on play symbol. 4.Tap on Stop Observation. | (00:00:00) Not shown. It should show same as frequency if data not recorded. | It should show same as frequency if data not recorded. Just blank. |  | High | 1 | New | Funcational | New Bug
CD_05 | Report and graph for duration method record is not correct. | On App's Dashboard 1.Tap on Reports and Graphs. 2.Tap on Duration demo-> More Details 3.Tap on chart. | Calculation wrong. | Calculation work fine. |  | High | 1 | New | Funcational | New Bug
CD_06 | In report section last added behavior should be on top | On App's Dashboard 1.Tap on Reports and Graphs. | Last added behavior shown last. | last added behavior should be shown on top. | NA | High | 1 | New | User Experience | New Bug
CD_07 | When schedule interval behavior created on the data recording method when set interval time it shown alert message. | On On App's Dashboard 1.Tap on Behaviour. 2.Tap on Plus Symbol. On Name and Detials, 3. Add valid details. On Data Recording Method, 4.Tap on Method Interval. 5.Tap on Method Settings. 6.Tap on From and To and select time. 7.Set Interval Time. | Alert message shown "Please set end time at least 10 min larger than start time." | If set time is valid than alert message not shown. And schedule interval behavior created. |  | High | 1 | New | Funcational | New Bug
CD_08 | Manual Interval demo purpose not work well. | 1.Set the interval time. (10 mins) 2.Now, Record the behaviour. (From 00:01:00 , TO : 00:10:00) 3.Change the device time.(00:09:00) 4.And see. | It not goes to next interval because server time is not passed interval | Set device time it is user friendly. |  | High | 1 | New | Requirement | New Bug
CD_09 | Ui Issue in report and graph. (Manual Interval) | On App's Dashboard 1.Tap on Reports and Graphs. 2.Tap on Manual Interval -> More Details. | In Recording method show method name : Interval. | In recording method show method name specific.i.e. Manual Interval. |  | Medium | 1 | New | User Experience | New Bug
CD_10 | Email Button not works | In the report section | It not works. | It should works well. |  | High | 1 | New | Requirement | New Bug
CD_11 | Logout button should be on Right corner | On App's Dashboard | It shows on left corner. | It shows on right corner |  | High | 1 | New | User Experience | New Bug
CD_12 | Time selection => 9.00 am to 1.00 pm => 12 should be shown as enabled | Create new Behavior 2.Select interval method. | 12.00 shows as disabled. | 12.00 shows as enabled. |  | High | 1 | New | User Experience | New Bug

## Defect Report Round3
| Rangam Technologies | Defect Report | [17 empty] | New Bug
Re-Open Bug
Start Date : | 20/09/2016 | Project: | ColorsKit - Life Skill Home/School Kit | End Date : | 21/09/2016 | [14 empty] | Suggestion
Tested by: | Bhavin | Platform: | Android | Round : | 3
Build Version: | 2.0.0 | Server: | Development
Device Version: | Samsung | OS: | 4.4
Defect Id | Defect Description | Steps to Reproduce | Actual Result | Expected Result | Attachments/Screen-shots | Severity | Priority | Status | Type | Type of Bug | User Interface Total | User Experience Total | Performance Total | Functional Total | Requirement Total | New BugTotal | Re-Open Bug Total | Suggestion Total | Total Bug
Reports and Graphs Module | [10 empty] | 2 | 5 | 0 | 5 | 0 | 11 | 1 | 0 | 12
CD_01 | In Mail report name (pdf name) not shown proper. | 1. Go to App and login with valid credentials. 2.Tap on Reports and Graphs. 3.Set filter accrding to user convience. 4.Tap on mail symbol. 5.Entervalid email address. 6.Send mail | It shows 1679.pdf | It should be shown as Report.pdf or as per Gerald's Feedback |  | High | 1 | New | User Experience | New Bug
CD_02 | Pdf not shown proper UI Issues. Respective change for individual report pdf. | 1.Send mail. 2.Download pdf. 3.Open pdf. | It shows UI issues. | UI issue should be shown proper. Respective change in print pdf also. |  | High | 1 | New | User Interface | New Bug
CD_03 | UI and spelling issue in individual frequency report. | 1.Go to app and login with valid credentials. 2.Tap on Reports and Graphs. 3.Tap on Frequency => More details arrow. 4.And see. | UI and Spellings mistakes are there. | UI and spellings should be correct. |  | High | 1 | New | User Interface | New Bug
CD_04 | Duration Graph not shown proper. | 1.Go to app and login with valid credentials. 2.Tap on Reports and Graphs. 3.Tap on Duration => More details arrow. 4.Tap on View Chart. | Graph not shown proper. | Graph shown proper. |  | High | 1 | New | Funcational | New Bug
CD_05 | Schedule Interval Report not shown proper. | 1.Go to app and login with valid credentials. 2.Tap on Reports and graphs. 3.Tap on Schedule Interval => More Details arrow. 4. And see. | Schedule Interval details not shown proper. | Details should be shown proper. |  | High | 1 | New | Funcational | New Bug
CD_06 | Schedule interval report shown proper. | 1.Go to app and login with valid credentials. 2.Tap on Reports and graphs. 3.Tap on Schedule Interval => More Details arrow. 4. And see. | If data not recorded than it also shown NA. | If data not recorded for particular time interval or rest of the interval than in list change the response message. Ie. "Not Observed". | NA | High | 1 | New | User Experience | New Bug
Edit/View Behaviors
CD_05 | As a user point of view user can't show what they enter. | 1.Go to App and login with valid credentials. 2.Tap on Edit/View Behaviors. 3.Tap on New Behavior. 4.Enter Behavior Name | When user tap on text box keyboard up and user can't show what they enter. | User show what they enter. |  | High | 1 | New | User Experience | New Bug
CD_06 | When edit behavior on "Name and Details" screen details show 255 characters allowed. But it already entered some words. | 1.Go to app and login with valid credentials. 2.Tap on Edit/View Behaviors. 3.Tap on New Behavior. 4.Create New Behavior. 5.Now edit that behavior and see. | Use already enterd words till it shows 255 character allowed. | Whatever words user enterd according to that character shown. |  | Medium | 1 | New | Funcational | New Bug
Solo Data Sheet
CD_07 | Spelling mistakes and date suggestion | 1.Go to app. 2.Frequency behavior created. 3.Assign freqquency behavior. 4.Go to solo data sheet. 5.Record Behavior. | Date is not user readabe. And speeling mistake. | Date should be proper user readable. And no speeling mistakes. |  | Medium | 1 | New | User Experience | New Bug
CD_08 | Schedule interval recording list not shown proper. | 1.Go to app. 2.Tap on Edit/View Behavior. 3.Tap on New Behavior. 4.Create new Behavior with schedule interval method. 5.Set time (1.30 AM to 5.20 AM). 6.Submit and Assign Behaavior to recording. 7.Tap on Solo Data Sheet. 8.And See. | User have schedule interval time is 1.30AM to 5.20 AM. But it shows in solo data sheet 1.30 to 4.30 only. | User select whatever interval it should be create exact difference time interval. |  | High | 1 | New | Funcational | New Bug
CD_09 | When Schedule interval recording at a time only one current interval time shown only. | 1.Go to app. 2.Create schedule interval behavior. 3.Assign behvaior. 4.Go to solo data sheet. 5.And see. | User shown all the interval time so its confusing. | User shown only current interval time only. Rest of the time interval no need to shown. |  | Medium | 1 | New | User Experience | New Bug
CD_10 | Manual interval not recorded properly. | 1.Go to app. 2.Create behavior with manual interval and interval time set 10 min. 3.Assign behvior.. 4.Tap on Solo data sheet. 5.See manual interval record. | It should not record exact 10 mins behavior. | It properly exact interval of time. | NA. | High | 1 | Re-opened | Funcational | Re-Open Bug

## dropdown (hidden)
list01 | list02 | list03 | list04 | list05 | list06 | list07 | list08 | list09 | list10 | list11
iOS | Time Card | Shahin | 1.0.0 | Development | High | 1 | New | Android | User Interface | Pass
Android | HEKXO App and Web | Hirendra | 1.1.1 | Staging | Medium | 2 | Open | 1.6 | User Experience | Fail
Web | ColorsKit - Admin | Yogesh | 1.1.2 | Production | Low | 3 | Re-opened | 2.1 | Performance | None
Kiosk | Rangam Consultants Inc. | Kedar | 1.1.3 |  |  |  | Closed | 2.2 | Funcational
| The Spectrum Careers (App and Web) |  | 1.1.4 |  |  |  | In discussion | 2.3 | Requirement
| OnBoarding App and Web |  | 1.1.5 |  |  |  |  | 3
| ColorsKit - Early Education School Kit |  | 1.1.6 |  |  |  |  | 4
| ColorsKit - Early Education Home Kit |  | 1.1.7 |  |  |  |  | 4.1
| ColorsKit - Life Skill Home/School Kit |  | 1.1.8 |  |  |  |  | 4.4
| The Spectrum Careers - UK (App and Web) |  | 1.1.9 |  |  |  |  | 5
| WebTeam Corp |  | 2.0.0 |  |  |  |  | 6
| Special Game Changer |  | 2.0.1 |  |  |  |  | 7
| Rangam Intranet |  | 2.0.2 |  |  |  |  | iOS
| Tricky Water |  | 2.0.3 |  |  |  |  | 4.4
| Rangam Infotech Pvt Ltd. |  | 2.0.4 |  |  |  |  | 4.5
| LetUsConnect |  | 2.0.5 |  |  |  |  | 4.6
| SAMHIN |  | 2.0.6 |  |  |  |  | 4.7
| Lapiz Lazooli |  | 2.0.7 |  |  |  |  | 4.8
| Haribhakti Trust |  | 2.0.8 |  |  |  |  | 4.9
| Staffing Bulletin |  | 2.0.9 |  |  |  |  | 4.1
| Rangam Staffing Pvt. Ltd. | [6 empty] | 5.1
| Jannya App and Web | [6 empty] | 5.2
| My Event Day (App and Web) | [6 empty] | 5.3
| Innovation and Technology | [6 empty] | 5.4
| ColorsKit Apps and Web | [6 empty] | 6.1
| ProCricket America | [6 empty] | 7.1
| SourcePros | [6 empty] | 7.2
| Client Work | [6 empty] | 9.1
| Organizational Operation | [6 empty] | 9.2
| Shanesh Colors (Kiosk/Colors Program) | [6 empty] | 9.3
| HEKXO Kickstarter | [6 empty] | 9.4
| In House Development Projct | [6 empty] | 9.5
| ColorsKit Supplemental Apps | [6 empty] | 9.6
HrTeamPlus
IAGSC
My Idea Portal
ColorsKit - MyToday
Other